## Test Scenarios
Test Scenario No. | Module | SubModule | Sub-Submodule | Sub-Sub-SubModule | Sub-Sub-Sub-SubModule | Test Scenario | Total Test Case | Priority | Planned Execution Date | Actual Execution Date
TS01 | User Management | Login | Mobile No. |  |  | Verify UI & functionality for the module
TS02 |  |  | Google |  |  | Verify UI & functionality for the module
TS03 |  |  | Facebook |  |  | Verify UI & functionality for the module
TS04 |  |  | Email |  |  | Verify UI & functionality for the module
|  |  | SignUp |  |  | Verify UI & functionality for the module
TS05 |  | Account Management | Account | Post Ad |  | Verify UI & functionality for the module
TS06 |  |  |  | Become a member |  | Verify UI & functionality for the module
TS07 |  |  |  | Favourites |  | Verify UI & functionality for the module
TS08 |  |  |  | Settings | Update Details | Verify UI & functionality for the module
TS09 |  |  |  |  | Delete Account | Verify UI & functionality for the module
TS10 |  |  |  |  | LogOut | Verify UI & functionality for the module
TS11 |  |  |  | Phone Numbers |  | Verify UI & functionality for the module
TS12 |  |  | Jobs | My Profile |  | Verify UI & functionality for the module
TS13 |  |  |  | Profile Database |  | Verify UI & functionality for the module
TS14 | Search |  |  |  |  | Verify UI & functionality for the module
TS15 | Footer | App Download | Google Play |  |  | Verify UI & functionality for the module
TS16 |  |  | App Store |  |  | Verify UI & functionality for the module
TS17 |  | Item Categories |  |  |  | Verify UI & functionality for the module
TS18 | Header | Chat |  |  |  | Verify UI & functionality for the module
TS19 |  | All Ads |  |  |  | Verify UI & functionality for the module
TS20 |  | Language |  |  |  | Verify UI & functionality for the module
TS21 |  | Quick Links |  |  |  | Verify UI & functionality for the module

## TestCase
Product Name |  |  | Bikroy | TC Start Date | 15/04/2023 | TC Execution Start Date | 17/04/2023 |  |  |  |  | TEST CASE
Developer Name |  |  | Saltside Technologies | TC End Date | 16/04/2023 | TC Execution End Date | 19/04/2023 |  |  |  |  | PASS | 40
|  |  |  | Test Case Developed By | Md. Golam An Nihal | Browser (tested) | Yes |  |  |  |  | FAIL | 6
|  |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | No |  |  |  |  | Not Executed | 0
Test Executed by | [11 empty] | Out of Scope | 0
[12 empty] | TOTAL | 46
#SL | Testcase ID | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 | TC01 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'Bikroy' 3. Goto the website |  |  | Passed
2 | TC02 | User Management | UI Testing | Signup | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 3. Check the spelling and grammar of the website |  |  | Passed
3 | TC03 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Check the font, text color and style |  |  | Passed
4 | TC04 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Hover over every fields |  |  | Passed
5 | TC05 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Check alignment of the fields |  |  | Passed
6 | TC06 |  | Functional Testing |  | Keeping mandatory fields blank | Should be as per the requirement | Sholud not allow user to register and pop an error message | N/A | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4.Keep mandatory fields blank |  |  | Passed
7 | TC07 |  |  |  | Checking Name field is case insensitive | Should accept the provided input | Found as per expectation | UxJvGuBan | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Input UxJvGuBan in name field |  |  | Passed
8 | TC08 |  |  |  | Checking alert message for all mandatory fields | Should pop an error message | Not found as per expectation | N/A | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Keeping blank in each field and checking repeatedly |  |  | Passed
9 | TC09 |  |  |  | Inputing name with special characters | Should not accept the provided input | Not found as per expectation | *&&&*()))) **###@%% | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter special characters in Name field | Special character error |  | Failed
10 | TC10 |  |  |  | Inputing Name with numbers | Should not accept the provided input | Not found as per expectation | 55555555 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter numbers in Name field | Numbers error |  | Failed
11 | TC11 |  |  |  | Inputing Name with decimal numbers | Should not accept the provided input | Not found as per expectation | 55.55.555 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter decimal numbers in Name field | Decimal numbers error |  | Failed
12 | TC12 |  |  |  | Inputing Name with alphanumeric characters | Should accept the provided input | Found as per expectation | Nihal55 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter alphanumeric characters in firstname and lastname field |  |  | Passed
13 | TC13 |  |  |  | Inputing Name with alphabets | Should accept the provided input | Found as per expectation | Md. Golam An Nihal | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter alphabets in firstname and lastname field |  |  | Passed
14 | TC14 |  |  |  | Entering comma between alphabets for Name | Should not accept the provided input | Not found as per expectation | An,Nihal | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4 Enter comma alphabets in Name field | Comma between alphabets error |  | Failed
15 | TC15 |  |  |  | Entering space between alphabets for Name | Should accept the provided input | Found as per expectation | Md. Golam An Nihal | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter space between alphabets in firstname and lastname field |  |  | Passed
16 | TC16 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | test@test.com | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Fill the email address with already registered email |  |  | Passed
17 | TC17 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found as per expectation with an error message | sjSJ@KDKJDSij | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Fill the email address with invalid email address format |  |  | Passed
18 | TC18 |  |  |  | Checking by inputing valid email format | Should accept the provided input | Found as per expectation | Email: annihal55@gmail.com | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Fill the email address with valid email address format |  |  | Passed
19 | TC19 |  |  |  | Checking password and confirm field values are masked | Should be masked | Found as per expectation | nihal12345 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter password and confirm password |  |  | Passed
20 | TC20 |  |  |  | Inputing invalid combinations of characters in password and confirm password field | Should not allow user to register and display a pop message | Found as per expectation | nihal12345 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter invalid combinations of characters in password and confirm password |  |  | Passed
21 | TC21 |  |  |  | Inputing weak password length | Should allow user to register | Found as per expectation | nihal | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter weak password length in password and confirm password |  |  | Passed
22 | TC22 |  |  |  | Inputing medium password length | Should allow user to register | Found as per expectation | nihal12345 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter medium password length in password and confirm password |  |  | Passed
23 | TC23 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation | hgjkgjkjkjh!&*77 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter strong password length in password and confirm password |  |  | Passed
24 | TC24 |  |  |  | Inputing different data for password and confirm password | Should not allow user to register and display a pop message | Found as per expectation | Password: nihal@555 Confirm password: nishat@555 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter different values in password and confirm password |  |  | Passed
25 | TC25 |  |  |  | Inputing valid data for password and confirm password | Should allow user to register | Found as per expectation | Password: nihal@555 Confirm password: nishat@556 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Enter valid credentals in password and confirm password |  |  | Passed
26 | TC26 |  |  |  | Checking registration with invalid email address | Should not allow user to register and pop an error message | Not found as per expectation | Name: Md. Golam An Nihal Email: ab@abc.com Password: nihal12345 Confirm Password: nihal12345 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 3. Fill all the fiels with invalid credentials | Invalid email address error |  | Failed
27 | TC27 |  |  |  | Checking registration button with valid credentials | Should allow user to register | Found as per expectation | Name: Md. Golam An Nihal Email: annihal55@gmail.com Password: nihal55@ Confirm Password: nihal55@ | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Fill all the fiels with valid credentials 5.Click 'Sign Up' |  |  | Passed
28 | TC28 |  |  |  | Checking confirmation mail sent to the registered email | Sent successfully | Found as per expectation | Name: Md. Golam An Nihal Email: annihal55@gmail.com Password: nihal55@ Confirm Password: nihal55@ | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Email' and then click on 'Sign up' at the bottom 4. Fill all the fiels with valid credentials 5.Click 'Sign Up' 6. Check mail and confirm account |  |  | Passed
29 | TC29 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | Md. Golam An Nihal | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Copy paste text in every field |  |  | Passed
30 | TC30 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Enter tab in every field |  |  | Passed
31 | TC31 |  | Functionality Testing | Login | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Keep both the fields blank |  |  | Passed
32 | TC32 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | nihal@55 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Input values in password field and check if it is masked |  |  | Passed
33 | TC33 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | Email:abc@test.com Password: hashasgsag | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Input invalid credentials in email and password field |  |  | Passed
34 | TC34 |  |  |  | Checking login valid credentials in email and password field | Should allow user to login | Found as per expectation | Email: annihal55@gmail.com Password: nihal55@ | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Input valid credentials in email and password field |  |  | Passed
35 | TC35 |  |  |  | Verifying ‘Forgot Password’ functionality | Should sent an email for recovering password | Found as per expectation | N/A | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3.Click on 'Forgot Password' 4. Check email |  |  | Passed
36 | TC36 |  |  |  | Checking by selecting ‘Forgot Password’ multiple times | Account should be temporarily restricted and a message should be displayed | Found as per expectation with a message | N/A | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3.Click on 'Forgot Password' multiple times |  |  | Passed
37 | TC37 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | Email: annihal55@gmail.com | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3.Click on 'Forgot Password' 4. Check the registered email |  |  | Passed
38 | TC38 |  |  |  | Verifying the functionality of 'Set a New Password' | Should provide a new input for setting new password | Found as per expectation | N/A | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' |  |  | Passed
39 | TC39 |  |  |  | Enabling the 'Show Password' checkbox of 'Set a New Password' | Password should be dispayed | Found as per expectation | Email: annihal55@gmail.com Password: nihal55@ | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enable 'Show Password' checkbox |  |  | Passed
40 | TC40 |  |  |  | Verifying inputing old password on 'Set a New Password' | Should not allow user to login and display an error message | Found as per expectation with an error message | Email: annihal55@gmail.com Password: nihal55@ | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter old password | input old password error |  | Failed
41 | TC41 |  |  |  | Verifying login with the newly changed password | Should allow user to login | Found as per expectation | Email: annihal55@gmail.com Password: nihal55@# | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on login |  |  | Passed
42 | TC42 |  |  |  | Checking if the link gets dissolved setting a new password | Link should get dissolved | Found as per expectation | N/A | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on 'Create New password' |  |  | Passed
43 | TC43 |  |  |  | Checking 'Continue with Facebook' | Should allow user to continue and login | Found as per expectation | Click on 'Continue with Facebook' | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue With Facebook' |  |  | Passed
44 | TC44 |  |  |  | Checking 'Continue with Google' | Should allow user to continue and login | Found as per expectation | Click on 'Continue with Google' | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue with Google' |  |  | Passed
45 | TC45 |  |  |  | Checking 'Continue with Mobile Number and OTP' | Should allow user to continue and login | Found as per expectation | 1701013335 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue with Mobile number and OTP' |  |  | Passed
46 | TC46 |  |  |  | Checking OTP validation and functionality | An OTP should be sent to the given Mobile number with a validation time for the OTP | Found as per expectation | 1701013335 | 1. Goto the URL https://www.bikroy.com/ 2. Click on 'Login' button at the top right corner 3. Click on 'Continue with Mobile number and OTP' 4. Check the incoming message for OTP and it's validation |  |  | Passed
47 |  |  |  | Improvement Scopes | 'Remember Me' checkbox should be available to the user
48 | TC47 |  | UI Testing | Account Management | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | Email: annihal55@gmail.com Password: nihal55@ | 1. Goto the URL https://www.bikroy.com/ 2. Login with valid credentials 3.Click on 'My Account" from the top right corner. 4. Check the spelling and grammar of the website |  |  | Passed
49 | TC48 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | Email: annihal55@gmail.com Password: nihal55@ | 1. Goto the URL https://www.bikroy.com/ 2. Login with valid credentials 3.Click on 'My Account" from the top right corner. 4. Check the font, text color and style |  |  | Passed
50 | TC49 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | Email: annihal55@gmail.com Password: nihal55@ | 1. Goto the URL https://www.bikroy.com/ 2. Login with valid credentials 3.Click on 'My Account" from the top right corner. 4. Check alignment of the fields |  |  | Passed
51 | TC50
52 | TC51 |  | Functionality Testing |  | Verifying post ad functionality for 'Mobiles' category for different locations.
53 | TC52 |  |  |  | Verifying post ad functionality for 'Electronics' category for different locations.
54 | TC53 |  |  |  | Verifying post ad functionality for 'Vehicles' category for different locations.
55 | TC54 |  |  |  | Verifying post ad functionality for 'Home & Living' category for different locations.
56 | TC55 |  |  |  | Verifying post ad functionality for 'Pets & Animals' category for different locations.
57 | TC56 |  |  |  | Verifying post ad functionality for 'Property' category for different locations.
58 | TC57 |  |  |  | Verifying post ad functionality for 'Women's Fashion & Beauty' category for different locations.
59 | TC58 |  |  |  | Verifying post ad functionality for 'Men's Fashion & Grooming' category for different locations.
60 | TC59 |  |  |  | Verifying post ad functionality for 'Hobbies, Sports & Kids' category for different locations.
61 | TC60 |  |  |  | Verifying post ad functionality for 'Business & Industry' category for different locations.
62 | TC61 |  |  |  | Verifying post ad functionality for 'Essentials' category for different locations.
63 | TC62 |  |  |  | Verifying post ad functionality for 'Education' category for different locations.
64 | TC63 |  |  |  | Verifying post ad functionality for 'Services' category for different locations.
65 | TC64 |  |  |  | Verifying post ad functionality for 'Agriculture' category for different locations.
66 | TC65
67 | TC66
68 | TC67
69 | TC68
70 | TC69
71 | TC70
72 | TC71
73 | TC72
74 | TC73
75 | TC74
76 | TC75
77 | TC76
78 | TC77
79 | TC78
80 | TC79
81 | TC80
82 | TC81
83 | TC82
84 | TC83
85 | TC84
86 | TC85
87 | TC86
88 | TC87
89 | TC88
90 | TC89
91 | TC90
92 | TC91
93 | TC92
94 | TC93
Negative test

## Report
Test Case Report
Project Name | Bikroy.com
Test Case Version | 1 |  |  |  |  | 40 | PASS
Written By | Sohanur Rahman |  |  |  |  | 6 | FAIL
Executed By | Sohanur Rahman |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 40 | 6 | 0 | 0 | 46
Grand Total | 40 | 6 | 0 | 0 | 46
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (46/46)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/46)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (40/46)*100 = 86.95
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (6/46)*100 = 13.04
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/46)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A